✈

FLIGHT SCHOOL

MANAGEMENT SYSTEM

INTERNSHIP PROJECT BREAKDOWN

For 27 Interns — Individual & Group Assignments

Version 1.0 — March 2026

8-Week Implementation Program

CONFIDENTIAL

# Table of Contents

1. Executive Summary

2. Project Overview

3. Team Structure (10 Teams, 27 Interns)

4. Individual Assignment Matrix

5. Detailed Team Breakdowns

5.1 Team T1: Planning & Scheduling

5.2 Team T2: Instructor App

5.3 Team T3: Records Keeping

5.4 Team T4: Analytics & Reporting

5.5 Team T5: Training Design Tool

5.6 Team T6: QMS — Qualifications

5.7 Team T7: DMS — Documents

5.8 Team T8: LMS — e-Learning

5.9 Team T9: Customization & Automation

5.10 Team T10: Integration & DevOps

6. Project Timeline & Milestones

7. Technology Stack

8. Evaluation Criteria

9. Communication & Workflow Guidelines

# 1. Executive Summary

This document defines the complete project breakdown for 27 interns tasked with building a Flight School Management System (FSMS) inspired by industry-standard aviation training platforms. The project is structured into 10 teams covering all functional modules, with each intern receiving clearly defined responsibilities, deliverables, and evaluation criteria.

The FSMS replicates the core feature set found in professional aviation training management software, including planning and scheduling, instructor tools, records keeping, analytics, training course design, qualification management (QMS), document management (DMS), learning management (LMS), customization options, and automated workflows.

# 2. Project Overview

| Project Name | Flight School Management System (FSMS) |
| --- | --- |
| Duration | 8 Weeks (March 3 – April 25, 2026) |
| Team Size | 27 Interns across 10 Teams |
| Technology | React.js, Node.js, Tailwind CSS, MySQL |
| Methodology | Agile Scrum — 2-week sprints with weekly standups |
| Repository | Monorepo with module-based folder structure |
| Deployment | Docker containerized, CI/CD via GitHub Actions |

# 3. Team Structure

The 27 interns are organized into 10 teams. Teams range from 2 to 3 members, each with a designated Team Lead responsible for coordination, code reviews, and milestone reporting.

| # | Team ID | Module | Members | Lead | Priority | Phase |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | T1 | Planning & Scheduling Module | 3 | I-01 | HIGH | Phase 1 |
| 2 | T2 | Instructor App Module | 3 | I-04 | HIGH | Phase 1 |
| 3 | T3 | Records Keeping Module | 3 | I-07 | HIGH | Phase 1 |
| 4 | T4 | Analytics & Reporting Module | 3 | I-10 | MEDIUM | Phase 2 |
| 5 | T5 | Training Design Tool | 3 | I-13 | MEDIUM | Phase 2 |
| 6 | T6 | QMS — Qualifications & Resources | 3 | I-16 | HIGH | Phase 1 |
| 7 | T7 | DMS — Document Management | 2 | I-19 | MEDIUM | Phase 2 |
| 8 | T8 | LMS — e-Learning Module | 2 | I-21 | MEDIUM | Phase 2 |
| 9 | T9 | Customization & Automated Flows | 3 | I-23 | LOW | Phase 3 |
| 10 | T10 | Integration, Testing & DevOps | 2 | I-26 | HIGH | All Phases |

# 4. Individual Assignment M5atrix

The following table maps every intern to their specific team, role, and primary responsibilities. Each intern has a unique ID (I-01 through I-27) for tracking.

| # | Intern ID | Team | Role | Primary Responsibilities |
| --- | --- | --- | --- | --- |
| 1 | I-01 | T1 | Team Lead / Frontend | Weekly calendar Gantt view, day/week/month toggle, drag-and-drop session placement, responsive layout |
| 2 | I-02 | T1 | Backend / Logic | Scheduling conflict detection algorithm, resource availability calculation, CRUD API endpoints, data validation |
| 3 | I-03 | T1 | UI/UX / Integration | Resource monitoring dashboard cards, filter/search components, forecasting simulation UI, notification integration |
| 4 | I-04 | T2 | Team Lead / UX | Instructor dashboard cards, session prep panel, lesson plan viewer with expandable sections |
| 5 | I-05 | T2 | Core Features | Grading tool with per-exercise scoring, grade calculation engine, debrief summary auto-generation logic |
| 6 | I-06 | T2 | Notes & Data | Real-time note-taking per exercise, training data collection forms, export functionality (PDF/CSV) |
| 7 | I-07 | T3 | Team Lead / Data | Trainee data model design, roster table with advanced filtering/sorting, data export (CSV/PDF) |
| 8 | I-08 | T3 | Profiles | Detailed trainee profile page, flight hours progress bar and stats, enrollment and status management |
| 9 | I-09 | T3 | Visualization | Competency radar chart (SVG/D3), grade history timeline, session records accordion view |
| 10 | I-10 | T4 | Team Lead / Charts | KPI stat cards, competency average bar charts, progress distribution visualization |
| 11 | I-11 | T4 | Advanced Analytics | Instructor consistency comparison algorithm, grading deviation analysis, trend lines and historical comparisons |
| 12 | I-12 | T4 | Dashboards | EBT/CBTA metrics panels, customizable filters and date range pickers, dashboard layout configuration |
| 13 | I-13 | T5 | Team Lead / Builder | Course creation wizard, session/exercise CRUD, course overview cards with stats |
| 14 | I-14 | T5 | Compliance | Compliance matrix visualization (grid with status indicators), regulatory standard definitions, auto-verification engine |
| 15 | I-15 | T5 | Management | Enrollment management, course version control, trainee assignment, export for authorities |
| 16 | I-16 | T6 | Team Lead / Core | Qualification data model, CRUD operations, filterable table with status pills, detail views |
| 17 | I-17 | T6 | Automation | Auto-renewal logic engine, expiry calculation, milestone-triggered updates, renewal verification rules |
| 18 | I-18 | T6 | Alerts & Resources | Notification/alert system for expirations, resource tracking dashboard, certificate PDF generation |
| 19 | I-19 | T7 | Team Lead / Core | Document library UI, search/filter/tag system, upload/download functionality, category management |
| 20 | I-20 | T7 | Permissions & Auto | Access control system, role-based visibility, auto-report generation and archiving, storage monitoring dashboard |
| 21 | I-21 | T8 | Team Lead / Courses | Course catalog UI, course cards with progress indicators, module list with lesson viewer, enrollment management |
| 22 | I-22 | T8 | Assessment & Tracking | Quiz engine with multiple question types, progress tracking system, completion certificates, analytics per module |
| 23 | I-23 | T9 | Team Lead / Customization | Theme engine with CSS variables, accent color system, language selector, dashboard builder UI |
| 24 | I-24 | T9 | Roles & Permissions | Role management CRUD, permission matrix editor, role-based UI rendering, user assignment interface |
| 25 | I-25 | T9 | Automation Engine | Workflow builder with trigger/action definitions, execution engine, run log and monitoring, API sync config |
| 26 | I-26 | T10 | Team Lead / Arch | App shell (sidebar, header, routing), global state store, cross-module event system, CI/CD pipeline setup |
| 27 | I-27 | T10 | QA & Docs | End-to-end test suite, integration testing across modules, deployment scripts, technical documentation, README |

# 5. Detailed Team Breakdowns

Each team breakdown includes scope, deliverables, individual task assignments, technology stack, acceptance criteria, and key dependencies.

5.1 Team T1: Planning & Scheduling Module

| TEAM SIZE 3 Interns | LEAD I-01 | PRIORITY HIGH | TIMELINE Phase 1 (Week 1–3) |
| --- | --- | --- | --- |

### Scope

Build the complete scheduling and resource management interface with weekly calendar, Gantt view, session management, resource availability monitoring, and conflict detection.

### Key Deliverables

• Weekly Gantt-style calendar view with drag-and-drop scheduling

• Resource availability dashboard (instructors, aircraft, simulators)

• Session CRUD operations with form validation

• Conflict detection engine (double-booking prevention)

• Filter and search functionality for schedules

• Forecasting and scenario simulation UI

### Individual Task Assignments

| Intern | Role | Specific Tasks & Deliverables |
| --- | --- | --- |
| I-01 | Team Lead / Frontend | Weekly calendar Gantt view, day/week/month toggle, drag-and-drop session placement, responsive layout |
| I-02 | Backend / Logic | Scheduling conflict detection algorithm, resource availability calculation, CRUD API endpoints, data validation |
| I-03 | UI/UX / Integration | Resource monitoring dashboard cards, filter/search components, forecasting simulation UI, notification integration |

### Technology Stack

React, date-fns, state management (Zustand/Redux), drag-and-drop library

### Acceptance Criteria

Calendar renders correctly, sessions can be created/edited/deleted, no double-booking allowed, resource counts update in real-time.

5.2 Team T2: Instructor App Module

| TEAM SIZE 3 Interns | LEAD I-04 | PRIORITY HIGH | TIMELINE Phase 1 (Week 1–3) |
| --- | --- | --- | --- |

### Scope

Digital tool for instructors to access lesson plans, take notes, grade exercises, and collect training data during and after sessions.

### Key Deliverables

• Instructor profile and dashboard view

• Session preparation panel with lesson plan viewer

• Real-time note-taking interface per exercise

• Interactive grading tool (1–5 scale) adapted to grading systems

• Session debrief summary auto-generation

• Training data collection and export

### Individual Task Assignments

| Intern | Role | Specific Tasks & Deliverables |
| --- | --- | --- |
| I-04 | Team Lead / UX | Instructor dashboard cards, session prep panel, lesson plan viewer with expandable sections |
| I-05 | Core Features | Grading tool with per-exercise scoring, grade calculation engine, debrief summary auto-generation logic |
| I-06 | Notes & Data | Real-time note-taking per exercise, training data collection forms, export functionality (PDF/CSV) |

### Technology Stack

React, rich text editor, PDF generation library, tablet-responsive design

### Acceptance Criteria

Instructors can view upcoming sessions, access lesson plans, take notes per exercise, submit grades within 60 seconds, and auto-generate debrief reports.

5.3 Team T3: Records Keeping Module

| TEAM SIZE 3 Interns | LEAD I-07 | PRIORITY HIGH | TIMELINE Phase 1 (Week 1–3) |
| --- | --- | --- | --- |

### Scope

Comprehensive trainee record system with profile management, flight hour tracking, competency progression, and historical data archiving.

### Key Deliverables

• Trainee roster with search, filter, and sort capabilities

• Detailed trainee profile with all training data

• Flight hours progress tracking with visual indicators

• Competency radar chart per trainee

• Historical session records and grade history

• Data export and archiving functionality

### Individual Task Assignments

| Intern | Role | Specific Tasks & Deliverables |
| --- | --- | --- |
| I-07 | Team Lead / Data | Trainee data model design, roster table with advanced filtering/sorting, data export (CSV/PDF) |
| I-08 | Profiles | Detailed trainee profile page, flight hours progress bar and stats, enrollment and status management |
| I-09 | Visualization | Competency radar chart (SVG/D3), grade history timeline, session records accordion view |

### Technology Stack

React, D3.js or SVG for charts, data table library, CSV/PDF export

### Acceptance Criteria

Full trainee profiles accessible in under 2 clicks, competency radar renders accurately, flight hours progress is visually clear, data exports work correctly.

5.4 Team T4: Analytics & Reporting Module

| TEAM SIZE 3 Interns | LEAD I-10 | PRIORITY MEDIUM | TIMELINE Phase 2 (Week 3–5) |
| --- | --- | --- | --- |

### Scope

Data visualization dashboards for competency tracking, instructor grading consistency, training KPIs, and EBT/CBTA metrics monitoring.

### Key Deliverables

• School-wide KPI dashboard (active trainees, completion rates, GPA)

• Competency average bar charts across all trainees

• Instructor grading consistency comparison

• Trainee progress distribution visualization

• EBT/CBTA metrics monitoring panels

• Customizable chart filters and date ranges

### Individual Task Assignments

| Intern | Role | Specific Tasks & Deliverables |
| --- | --- | --- |
| I-10 | Team Lead / Charts | KPI stat cards, competency average bar charts, progress distribution visualization |
| I-11 | Advanced Analytics | Instructor consistency comparison algorithm, grading deviation analysis, trend lines and historical comparisons |
| I-12 | Dashboards | EBT/CBTA metrics panels, customizable filters and date range pickers, dashboard layout configuration |

### Technology Stack

React, Recharts or Chart.js, D3.js, data aggregation utilities

### Acceptance Criteria

All charts render correctly with real data, filters update charts dynamically, grading consistency metrics are statistically valid.

5.5 Team T5: Training Design Tool

| TEAM SIZE 3 Interns | LEAD I-13 | PRIORITY MEDIUM | TIMELINE Phase 2 (Week 3–5) |
| --- | --- | --- | --- |

### Scope

Course builder for creating training programs with sessions, exercises, compliance matrices, and regulatory standard verification.

### Key Deliverables

• Course builder with session and exercise creation

• Drag-and-drop session ordering within courses

• Interactive compliance matrix (EASA Part-FCL, NAA)

• Enrollment and course management

• Automatic version control and archiving

• Regulatory standard verification engine

### Individual Task Assignments

| Intern | Role | Specific Tasks & Deliverables |
| --- | --- | --- |
| I-13 | Team Lead / Builder | Course creation wizard, session/exercise CRUD, course overview cards with stats |
| I-14 | Compliance | Compliance matrix visualization (grid with status indicators), regulatory standard definitions, auto-verification engine |
| I-15 | Management | Enrollment management, course version control, trainee assignment, export for authorities |

### Technology Stack

React, drag-and-drop, JSON schema for course structure, compliance rule engine

### Acceptance Criteria

Courses can be created with sessions and exercises, compliance matrix accurately reflects regulatory coverage, version history is maintained.

5.6 Team T6: QMS — Qualifications & Resources

| TEAM SIZE 3 Interns | LEAD I-16 | PRIORITY HIGH | TIMELINE Phase 1 (Week 1–3) |
| --- | --- | --- | --- |

### Scope

Qualification Management System for tracking certifications, expiry dates, auto-renewal logic, and resource availability monitoring.

### Key Deliverables

• Qualification database with full CRUD

• Expiry date tracking with color-coded status (valid/expiring/expired)

• Auto-renewal logic triggered by training milestones

• Notification system for upcoming expirations

• Certificate and competency tracking per person

• Resource tracking dashboard (aircraft, simulators)

### Individual Task Assignments

| Intern | Role | Specific Tasks & Deliverables |
| --- | --- | --- |
| I-16 | Team Lead / Core | Qualification data model, CRUD operations, filterable table with status pills, detail views |
| I-17 | Automation | Auto-renewal logic engine, expiry calculation, milestone-triggered updates, renewal verification rules |
| I-18 | Alerts & Resources | Notification/alert system for expirations, resource tracking dashboard, certificate PDF generation |

### Technology Stack

React, date computation library, notification system, PDF generation

### Acceptance Criteria

All qualifications tracked with correct expiry status, auto-renewal triggers correctly on milestone completion, alerts fire 30/60/90 days before expiry.

5.7 Team T7: DMS — Document Management

| TEAM SIZE 2 Interns | LEAD I-19 | PRIORITY MEDIUM | TIMELINE Phase 2 (Week 3–5) |
| --- | --- | --- | --- |

### Scope

Document Management System with file storage, access controls, auto-generation of session reports, and self-service upload for trainees and instructors.

### Key Deliverables

• Document library with search, category filters, and tags

• File upload/download with drag-and-drop

• Access permission system (Restricted/Staff/All)

• Auto-generated session reports archived automatically

• Self-service document upload for trainees and instructors

• Storage usage monitoring

### Individual Task Assignments

| Intern | Role | Specific Tasks & Deliverables |
| --- | --- | --- |
| I-19 | Team Lead / Core | Document library UI, search/filter/tag system, upload/download functionality, category management |
| I-20 | Permissions & Auto | Access control system, role-based visibility, auto-report generation and archiving, storage monitoring dashboard |

### Technology Stack

React, file handling APIs, role-based access control, PDF auto-generation

### Acceptance Criteria

Documents can be uploaded, searched, filtered, and downloaded; access restrictions enforced correctly; auto-reports generated on session completion.

5.8 Team T8: LMS — e-Learning Module

| TEAM SIZE 2 Interns | LEAD I-21 | PRIORITY MEDIUM | TIMELINE Phase 2 (Week 3–5) |
| --- | --- | --- | --- |

### Scope

Learning Management System for creating and delivering e-learning courses, tracking trainee progress through modules, and managing enrollments.

### Key Deliverables

• Course catalog with enrollment management

• Module/lesson viewer with progress tracking

• Progress rings and completion percentages per course

• Quiz/assessment engine for knowledge verification

• Trainee progress dashboard per course

• Course completion certificates

### Individual Task Assignments

| Intern | Role | Specific Tasks & Deliverables |
| --- | --- | --- |
| I-21 | Team Lead / Courses | Course catalog UI, course cards with progress indicators, module list with lesson viewer, enrollment management |
| I-22 | Assessment & Tracking | Quiz engine with multiple question types, progress tracking system, completion certificates, analytics per module |

### Technology Stack

React, video player integration, quiz engine, progress state management

### Acceptance Criteria

Courses display with accurate progress, quizzes can be taken and graded, completion is tracked and certificates generated.

5.9 Team T9: Customization & Automated Flows

| TEAM SIZE 3 Interns | LEAD I-23 | PRIORITY LOW | TIMELINE Phase 3 (Week 5–7) |
| --- | --- | --- | --- |

### Scope

Interface customization (themes, colors, language, roles) and automated workflow engine for notifications, report generation, data sync, and compliance monitoring.

### Key Deliverables

• Theme engine (dark/light/auto) with accent color picker

• User roles and permissions management UI

• Custom dashboard builder

• Automated workflow builder with trigger/action pairs

• Workflow execution log and monitoring

• Third-party API sync configuration

### Individual Task Assignments

| Intern | Role | Specific Tasks & Deliverables |
| --- | --- | --- |
| I-23 | Team Lead / Customization | Theme engine with CSS variables, accent color system, language selector, dashboard builder UI |
| I-24 | Roles & Permissions | Role management CRUD, permission matrix editor, role-based UI rendering, user assignment interface |
| I-25 | Automation Engine | Workflow builder with trigger/action definitions, execution engine, run log and monitoring, API sync config |

### Technology Stack

React, CSS custom properties, workflow state machine, cron-like scheduler, REST API integration

### Acceptance Criteria

Theme changes apply globally and persist, role permissions restrict UI correctly, automated workflows trigger and execute correctly with logging.

5.10 Team T10: Integration, Testing & DevOps

| TEAM SIZE 2 Interns | LEAD I-26 | PRIORITY HIGH | TIMELINE All Phases (Week 1–8) |
| --- | --- | --- | --- |

### Scope

Cross-module integration, navigation shell, global state management, end-to-end testing, CI/CD pipeline, deployment, and documentation.

### Key Deliverables

• App shell with sidebar navigation and header

• Global state management setup (user session, notifications)

• Cross-module data flow and event bus

• End-to-end test suite covering all modules

• CI/CD pipeline configuration

• Technical documentation and API docs

### Individual Task Assignments

| Intern | Role | Specific Tasks & Deliverables |
| --- | --- | --- |
| I-26 | Team Lead / Arch | App shell (sidebar, header, routing), global state store, cross-module event system, CI/CD pipeline setup |
| I-27 | QA & Docs | End-to-end test suite, integration testing across modules, deployment scripts, technical documentation, README |

### Technology Stack

React Router, Zustand/Redux, Playwright/Cypress, GitHub Actions, Docker

### Acceptance Criteria

All modules accessible via sidebar, global state persists across navigation, all tests pass, app deploys successfully, documentation is complete.

# 6. Project Timeline & Milestones

The project follows a phased approach over 8 weeks with 4 key milestones.

| Phase | Duration | Activities | Teams Active |
| --- | --- | --- | --- |
| Phase 1 | Week 1–3 | Core module development: Planning, Instructor App, Records, QMS. Integration shell setup. | T1, T2, T3, T6, T10 |
| Milestone 1 | End of Week 3 | Core modules demo-ready. Individual code reviews. | All |
| Phase 2 | Week 3–5 | Secondary modules: Analytics, Training Design, DMS, LMS. Cross-module integration. | T4, T5, T7, T8, T10 |
| Milestone 2 | End of Week 5 | All modules functional. Integration testing begins. | All |
| Phase 3 | Week 5–7 | Smart features: Customization, Automation, polish, testing, documentation. | T9, T10, All (polish) |
| Milestone 3 | End of Week 7 | Feature freeze. Full E2E testing. Bug fixing. | All |
| Phase 4 | Week 8 | Final testing, documentation, demo prep, individual presentations. | All |
| Milestone 4 | End of Week 8 | Final demo day. Individual evaluations. Project handoff. | All |

# 7. Technology Stack

| Layer | Technology | Purpose |
| --- | --- | --- |
| Frontend | React 18 + Vite | Component-based UI framework with fast HMR |
| Styling | Tailwind CSS | Utility-first CSS for rapid, consistent styling |
| State Mgmt | Zustand or Redux Toolkit | Global state for cross-module data sharing |
| Charts | Recharts + D3.js | Data visualization for analytics and dashboards |
| Backend | Node.js + Express | REST API server for data operations |
| Database | MySQL | Relational database for structured aviation data |
| ORM | Prisma | Type-safe database client with migrations |
| Auth | JWT + bcrypt | Authentication and role-based access control |
| Testing | Vitest + Playwright | Unit testing and end-to-end browser testing |
| CI/CD | GitHub Actions | Automated testing and deployment pipelines |
| Containers | Docker + Docker Compose | Consistent development and deployment environments |
| Docs | Storybook + JSDoc | Component documentation and code comments |

# 8. Evaluation Criteria

Each intern will be evaluated individually based on the following weighted criteria:

| # | Criteria | Weight | Description |
| --- | --- | --- | --- |
| 1 | Code Quality | 20% | Clean, well-structured, documented code following project conventions. Meaningful variable names, proper component decomposition. |
| 2 | Feature Completion | 25% | All assigned deliverables implemented and functional per acceptance criteria. Edge cases handled. |
| 3 | UI/UX Quality | 15% | Polished, responsive interface consistent with the overall design system. Attention to detail. |
| 4 | Collaboration | 15% | Effective communication with team, timely PR reviews, constructive feedback, conflict resolution. |
| 5 | Testing | 10% | Unit tests for critical functions, integration tests for module interfaces, edge case coverage. |
| 6 | Documentation | 5% | Component docs, API docs, README contributions, inline code comments. |
| 7 | Presentation | 10% | Final demo quality, ability to explain design decisions and technical trade-offs clearly. |

# 9. Communication & Workflow Guidelines

### Daily Standups

Each team holds a 15-minute daily standup covering: what was completed yesterday, what is planned for today, and any blockers. The Integration team (T10) attends all standups on rotation.

### Git Workflow

• Main branch: protected, deploy-ready at all times

• Feature branches: named as feature/T{team}-{feature-name}

• Pull Requests: minimum 1 reviewer from same team, 1 from T10

• Commit messages: follow Conventional Commits (feat:, fix:, docs:, etc.)

• Code review turnaround: 24 hours maximum

### Sprint Ceremonies

• Sprint Planning (Monday, Week 1, 3, 5, 7): 1 hour, all teams

• Sprint Review/Demo (Friday, Week 2, 4, 6, 8): 1 hour, all teams present progress

• Retrospective (Friday, Week 2, 4, 6, 8): 30 minutes after review

• Cross-team sync (Wednesday): 30 minutes, team leads + T10

### Definition of Done

• Feature implemented and self-tested

• Unit tests written and passing (minimum 80% coverage for critical functions)

• Code reviewed and approved by at least 1 peer

• No console errors or warnings

• Responsive design verified (desktop + tablet)

• Documentation updated (JSDoc, README)

• Integration tested with dependent modules

END OF PROJECT BREAKDOWN DOCUMENT For questions or clarifications, contact the Project Manager.